## Gantt Chart
M.A.R.S. Agile Transformation — 20-Week Engagement Gantt
| Phase 1: Kickoff |  | Phase 2: Foundation |  |  |  |  | Phase 3: Building
Lane | Wk 0 Feb 23 | Wk 1 Mar 2 | Wk 2 Mar 9 | Wk 3 Mar 16 | Wk 4 Mar 23 | Wk 5 Mar 30 | Wk 6 Apr 6 | Wk 7 Apr 13 | Wk 8 Apr 20 | Wk 9 Apr 27 | Wk 10 May 4 | Wk 11 May 11 | Wk 12 May 18 | Wk 13 May 25 | Wk 14 Jun 1 | Wk 15 Jun 8 | Wk 16 Jun 15 | Wk 17 Jun 22 | Wk 18 Jun 29 | Wk 19 Jul 6 | Wk 20 Jul 13
Training |  | Agile Mindset ✅ Scrum Fund. 🔒 R&R ✅ Achieving Flow |  | Intro to Pre-Planning |  | Estimation (T) HOLD: Apr 2 | DoD/DoR Pt 1 (T) | DoD/DoR Pt 2 (T) User Stories (F) Backlog Writing (T) | Backlog Writing (T) HOLD: Apr 20 | Adaptability (F) Story Splitting (F) |  | Flow/WIP (LT) Product Mindset (LT) |  | Navigating Change (C,F) |  | On-Demand modules | Triggered training | Adapt/Change/Psych HOLD: Jun 25
Coaching | Manager Discovery Onboarding |  | Team Coaching begins Office Hours daily | Embedded coaching PL 1:1 intros | Office Hours begins Pre-plan coaching | Pre-plan coaching 30-60-90 plans | Pre-plan readout Leader debrief |  | Sprint execution Dependency mgmt | WIP/flow coaching | Deepening practices | WIP/flow coaching | PI #1 readiness | Midpoint retro | Self-sufficiency shift | Ongoing coaching | Self-coaching | Maturity assessments | Sustainability plan | Maturity assessments | Engagement wrap Final debrief
Jira |  |  | Initial onboard | Deep dives by team | Findings & recs | Job aides & standards | Dashboards v1 |  | Baseline velocity | Scorecards v1 Dashboard builds | Scorecards v1 Dashboard builds | Scorecards v1 Dashboard builds | JIRA migration | Metrics review | Metrics playbook | Final playbook |  |  |  |  | Final handoff
OCM | Pre-training comms Surveys out |  | Baseline pulse Manager 1:1s | JIRA/standardization comms | Plans comms JIRA basics comms |  | Ongoing OCM |  |  |  | Pulse Check #2 | [8 empty] | Pulse Check #3 Final
Milestones |  |  | Greg & Gino Weekly |  | Greg & Gino Weekly |  | PRE-PLANNING Greg & Gino Weekly |  | Greg & Gino (bi-wk) |  | Greg & Gino (bi-wk) |  |  | PI PLANNING #1 Greg & Gino Weekly | [6 empty] | PI PLANNING #2 Engagement Close
Legend: | Training | Coaching | Jira | OCM | Milestones
✅ = Complete ¦ 🔒 = Locked ¦ (T) = Team Session ¦ (F) = Formal ¦ (LT) = Leadership Team ¦ (C) = Coaching
Prepared by Turnberry Solutions · Subaru M.A.R.S. Agile Transformation · Updated Mar 18, 2026